## Scrum definition
CONCEPTS | Open Assessement | Scrum Guide | Personal notes
SCRUM | A framework within which complex products in complex environments are developed | Scrum is not a process or a technique for building products; rather, it is a framework within which you can employ various processes and techniques. The Scrum framework consists of a set of Scrum Teams and their associated roles; Time-Boxes, Artifacts, and Rules.
| An organization has decided to adopt Scrum, but management wants to change the terminology to fit with terminology already used. What will likely happen if this is done-> Without a new vocabulary as a reminder of the change, very little change may actually happen AND The organization may not understand what has changed within Scrum and the benefits of Scrum may be lost AND Management may feel less anxious | Scrum, which is grounded in empirical process control theory, employs an iterative, incremental approach to optimize predictability and control risk. Three pillars uphold every implementation of empirical process control
There is no role called "project manager" in Scrum
Management external to Scrum has no role.
Rules |  | Rules bind together Scrum’s time-boxes, roles, and artifacts. Its rules are described throughout the body of this document. For example, it is a Scrum rule that only Team members - the people committed to turning the Product Backlog into an increment – can talk during a Daily Scrum.
Scrum Artifacts |  | Scrum Artifacts include the Product Backlog, the Release Burndown, the Sprint Backlog, and the Sprint Burndown.
Time Boxes |  | The Time-Boxes in Scrum are the Release Planning Meeting, the Sprint, the Sprint Planning Meeting, the Sprint Review, the Sprint Retrospective, and the Daily Scrum.
Emerging Requirements |  |  | As contrasted to waterfall model
Adaptive approach

## Team
CONCEPTS | Open Assessement | Scrum Guide
Team |  | Scrum Team members are called “pigs.”
Who is scrum team ? | The Scrum Team consists of the Scrum Master (manage the process) the Product Owner (manage what to do) and the Team (doing what the Product Owner wants within the process). | Scrum Teams are designed to optimize flexibility and productivity; to this end, they are self-organizing, they are cross-functional, and they work in iterations
| Turn the Product Backlog it selects into an increment of potentially shippable product functionality | The optimal size for a Team is seven people, plus or minus two.
Team membership | Change: As needed, while taking into account short term reduction in Team productivity | Team composition may change at the end of a Sprint. Every time Team membership is changed, the productivity gained from self-organization is diminished. Care should be taken when changing Team composition.

## Scrum master
CONCEPTS | Open Assessement | Scrum Guide
Scrum master | Is a Management Position | The ScrumMaster should never be the Product Owner
Should NOT act as go-between team and product owner
| The primary way a Scrum Master keeps a team working at its highest level of productivity -> By facilitating team decisions and removing impediments | The ScrumMaster is responsible for ensuring that the Scrum Team adheres to Scrum values, practices, and rules. The ScrumMaster helps the Scrum Team and the organization adopt Scrum.
Impediments | Resolve:Prioritize the list and work on them in order; Alert management to the impediments and their impact; Consult with the team.

## Product Owner
CONCEPTS | Open Assessement | Scrum Guide
Product Owner (PO) | The PO knows the most about the progress toward a business objective or a release, and is able to explain the alternatives most clearly | The Product Owner is the one and only person responsible for managing the Product Backlog and ensuring the value of the work the Team performs.
| Responsibility: Optimizing the return on investment of the work | The Product Owner is present during the second part of the Sprint Planning Meeting to clarify the Product Backlog and to help make trade-offs.

## Product Backlog
CONCEPTS | Open Assessement | Scrum Guide
Product Backlog | Multiple teams: ONE product backlog (Projects have an overall product owner, regardless of how many teams are used. The overall Product Owner must able to assess the progress in turning the Product Backlog into usable functionality. To do so, the overall Product Owner must see the integrated, complete “done” of all people working on the project. Otherwise, the undone work is indeterminate.) | Scrum employs four principal artifacts. The Product Backlog is a prioritized list of everything that might be needed in the product.
| How much work must a Team do to a Product Backlog item it selects for a Sprint-> As much as it has told the Product Owner will be done for every Product Backlog item it selects in conformance with the definition of done. | The Product Owner is responsible for the Product Backlog, its contents, its availability, and its prioritization. Product Backlog is never complete.
| Sorted by: Least valuable items at the bottom to most valuable at the top | It is a list of all features, functions, technologies, enhancements, and bug fixes that constitute the changes that will be made to the product for future releases. Priority is driven by risk, value, and necessity.
Burndown chart & | Tracks: Work remaining across time | The various aspects of the process must be inspected frequently enough so that unacceptable variances in the process can be detected.
Release Burndown |  | A Release Burndown measures remaining Product Backlog across the time of a release plan.
Release Planning Meeting |  | The release plan establishes the goal of the release, the highest priority Product Backlog, the major risks, and the overall features and functionality that the release will contain.
Release planning is entirely optional.
In Scrum release planning, an overall goal and probable outcomes are defined.
Release planning requires estimating and prioritizing the Product Backlog for the Release.

## Sprint
CONCEPTS | Open Assessement | Scrum Guide
Sprint | No firm prerequisites (release plan, staffing, product backlog); The TEAM updates the TASK estimates; | The heart of Scrum is a Sprint, which is an iteration of one month or less that is of consistent length throughout a development effort. All Sprints use the same Scrum framework, and all Sprints deliver an increment of the final product that is potentially releasable. One Sprint starts immediately after the other.
| What is the maximum length of a Sprint? Not so long that the risk is unacceptable to the Product Owner AND Not so long that other business events can't be readily synchronized with the development work AND One calendar month | Sprints contain and consist of the Sprint Planning meeting, the development work, the Sprint Review, and the Sprint Retrospective. Sprints occur one after another, with no time in between Sprints.
| Does NOT do during first sprint: Nail down the complete architecture and infrastructure AND Develop a plan for the rest of the project | A Sprint is an iteration. Sprints are time-boxed.
Do do during first sprint: Develop and deliver at least one piece of functionality AND Deliver an increment of potentially shippable functionality
Sprint Burndown |  | A Sprint Burndown measures remaining Sprint Backlog items across the time of a Sprint.
Sprint Backlog |  | The Sprint Backlog is a list of tasks to turn the Product Backlog for one Sprint into an increment of potentially shippable product.
Only the Team can change its Sprint Backlog during a Sprint. Only the Team can change the contents or the estimates. The Sprint Backlog is a highly visible, real time picture of the work that the Team plans to accomplish during the Sprint, and it belongs solely to the Team.
The Sprint Backlog consists of the tasks the Team performs to turn Product Backlog items into a “done” increment.
Sprint Backlog Item | All Sprint Backlog Items are "owned" by the entire Team, even though each one may be done by an individual team member. | One day or less is a usual size for a Sprint Backlog item that is being worked on.
Adjust sprint | who has to be present when reviewing and adjusting the Sprint goal and work -> The Product Owner and Team | Sprints can be cancelled before the Sprint time box is over. Only the Product Owner has the authority to cancel the Sprint
Abnormal termination of a Sprint -> When the Product Owner determines that it makes no sense to finish it
Visualizations
(Courtesy of Jeff Sutherland)

## Sprint Meetings
CONCEPTS | Open Assessement | Scrum Guide
Sprint planning meeting | 8 hours for a monthly Sprint, proportionately less for shorter Sprints | The Sprint Planning meeting is when the iteration is planned. It is time-boxed to eight hours for a one month Sprint.
There are two parts to the Sprint Planning Meeting: the “What?” part and the “How?” part.
The amount of backlog the Team selects is solely up to the Team. Only the Team can assess what it can accomplish over the upcoming Sprint. Having selected the Product Backlog, a Sprint Goal is crafted.
While designing, the Team identifies tasks. These tasks are the detailed pieces of work needed to convert the Product Backlog into working software. Tasks should have decomposed so they can be done in less than one day. This task list is called the Sprint Backlog.
Sprint review |  | In addition, the Sprint Review and Planning meetings are used to inspect progress toward the Release Goal and to make adaptations that optimize the value of the next Sprint
At the end of the Sprint, a Sprint Review meeting is held. This is a four hour time-boxed meeting for one month Sprints. For Sprints of lesser duration, allocate proportionately less of the total Sprint length to this meeting
The Sprint Review provides valuable input to subsequent Sprint Planning meeting.
Sprint retrospective |  | Finally, the Sprint Retrospective is used to review the past Sprint and determine what adaptations will make the next Sprint more productive, fulfilling, and enjoyable.
After the Sprint Review and prior to the next Sprint Planning meeting, the Scrum Team has a Sprint Retrospective meeting. This is a three hour, time-boxed meeting for monthly Sprints
The purpose of the Retrospective is to inspect how the last Sprint went in regards to people, relationships, process and tools. The inspection should identify and prioritize the major items that went well and those items that-if done differently-could make things even better.

## Daily Scrum
CONCEPTS | Open Assessement | Scrum Guide
Daily Scrum | Scrum master: does not have to be there; he or she only has to ensure the Team has a Daily Scrum; the TEAM is required ! | The Daily Scrum meeting is used to inspect progress toward the Sprint goal, and to make adaptations that optimize the value of the next work day.
| Daily Scrum held at the same time and same place -> The consistency reduces complexity | During the meeting, each Team member explains: 1. What he or she has accomplished since the last meeting; 2. What he or she is going to do before the next meeting; and 3. What obstacles are in his or her way.
| Timebox: 15 minutes | The ScrumMaster ensures that the Team has the meeting. The Team is responsible for conducting the Daily Scrum.
The Daily Scrum is an inspection of the progress toward that Sprint Goal

## DONE
CONCEPTS | Open Assessement | Scrum Guide
DONE
| Many teams: All Teams must have a definition of "done" that when their work integrates results in a definition of "done" that is potentially shippable. | Transparency ensures that aspects of the process that affect the outcome must be visible to those managing the outcomes. Not only must these aspects be transparent, but also what is being seen must be known. That is, when someone inspecting a process believes that something is done; it must be equivalent to their definition of done.
When someone describes something as done, everyone must understand what done means.
A completely “done” increment includes all of the analysis, design, refactoring, programming, documentation and testing for the increment and all Product Backlog items in the increment.
“Undone” work is added to a Product Backlog item named “undone work” so it accumulates and correctly reflects on the Release Burndown graph. This technique creates transparency in progress toward a release.

## Internet links
CONCEPTS | Links
Basics | www.scrumfoundation.com (where classes are offered)
www.scrum.org (website by Ken Schwaber)
Video | http://www.youtube.com/watch?v=vmGMpME_phg (short film about Scrum basics)
http://www.youtube.com/watch?v=q3t8twm3aUk (longer film about Scrum basics and why Scrum is so hard)
http://www.youtube.com/watch?v=B3htbxIkzzM (short film about dysfunctional daily scrum)
http://www.youtube.com/watch?v=1RmCahV3Tbw (Jeff Sutherland on the evolution of Scrum)
http://video.google.com/videoplay?docid=-7230144396191025011 (Ken Schwabers 1 hour video)
http://www.youtube.com/watch?v=u6XAPnuFjJc&feature=autofb (8 min animation about motivation)
Websites | www.scrumalliance.org (scrum umbrella site)
www.jeffsutherland.com (Jeff Sutherland's site)
www.gertrudandcope.com (Gertrud and Cope)
www.xprogramming.com (Ron Jeffries site)
www.estherderby.com (Esther Derby’s site)
www.mountaingoatsoftware.com (Mike Cohn's site)
http://www.planningpoker.com/ (play planning poker online)
Papers | Buy and download the original Scrum paper (This is where Scrum is first mentioned for development and is a strong influent to Scrum as we know it today)
http://harvardbusinessonline.hbsp.harvard.edu/b01/en/common/item_detail.jhtml?id=86116
Buy and download “A Leader’s Framework for Decision Making”. Give it to your boss and make sure he/she reads it.
http://harvardbusinessonline.hbsp.harvard.edu/b01/en/common/item_detail.jhtml;jsessionid=PPE1GJXYQAYPUAKRGWDSELQBKE0YIISW?id=R0711C&referral=7855
The Scrum Primer (a short and describable version of Scrum)
http://scrumtraininginstitute.com/home/stream_download/scrumprimer